## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-00 | Learning the Python Libraries | MUST HAVE | Python | All Team | 3- Completed
S2 | S2 | US-01 | Gathering dataset for traffic violation from Kaggle and validate it. | MUST HAVE | Kaggle Account | All Team | 3- Completed
S3 | S3 | US-02 | Home and About Pages for project info | MUST HAVE | Streamlit | Laasya Kadali | 3- Completed
S4 | S4 | US-03 | Initiation and Dashboard/Overview | MUST HAVE | Streamlit | Chandana BC | 3- Completed
S5 | S5 | US-04 | ​Environment Impact Analysis | MUST HAVE | Python Libraries | Vinay Manda | 3- Completed
S6 | S6 | US-05 | Time and Trend Analysis | MUST HAVE | Python Libraries | Khushi Bhandari | 3- Completed
S7 | S7 | US-06 | Driver Behaviour Analysis | MUST HAVE | Python Libraries | Krti Gautam | 3- Completed
S8 | S8 | US-07 | ​Vehicle Analysis | MUST HAVE | Python Libraries | Vanshika Jain | 3- Completed
S9 | S9 | US-08 | ​Payment Trend Analysis | MUST HAVE | Python Libraries | Sonika Ammanbrolu | 3- Completed
S10 | S10 | US-09 | ​Map Visualization | MUST HAVE | Folium | Niharika Raut | 3- Completed
S11 | S11 | US-10 | Reports and About | MUST HAVE | Python | Naga Josna Tadilboaina | 3- Completed
S12 | S12 | US-11 | Data Preprocessing | MUST HAVE | CSV | Gauri Joshi | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 52 | 6 | 6 | 8 | 9 | 7 | 0 | 0 | 3 | 4 | 5 | 4 | 4 | 8 | 2
SPRINT 1 BACKLOG
US-00 | T-101 | Python/Numpy Learning | 2025-11-14 | 2025-11-21 | All | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-00 | T-102 | Python/Pandas Learning | 2025-11-24 | 2025-11-30 | All | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-00 | T-103 | Assignment on Numpy and Pandas | 2025-12-01 | 2025-12-01 | All | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0
US-00 | T-104 | Python/Matplot Learning | 2025-12-03 | 2025-12-08 | All | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
US-00 | T-105 | Assignment on Numpy, Pandas and Matplot | 2025-12-09 | 2025-12-09 | All | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
SPRINT 2 BACKLOG
US-01 | T-201 | Python/Seaborn Learning | 2025-12-10 | Coding | 3- Completed | Coding | 3- Completed | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-202 | Assignment on Seaborn Library | 2025-12-15 | Coding | 3- Completed | Coding | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-203 | Working on Dataset using Python Libraries | 2026-12-16 | Coding | 3- Completed | Coding | 3- Completed | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-204 | Streamlit Learning | 2026-12-22 | Coding | 3- Completed | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
US-04 | T-205 | Project Ideation | 2026-12-21 | Coding | 3- Completed | Design | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
p
US-04 | T-301 | Data Processing | 2025-12-22 | Build | 3- Completed | Unit Test | 3- Completed | 3 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-302 | Initiation and Dashboard/Overview | 2026-12-23 | Build | 3- Completed | Build | 3- Completed | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-303 | Home and About Page Creation | 2026-12-24 | Build | 3- Completed | Build | 3- Completed | 3 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-304 | Analysis using Libraries | 2026-12-26 | Build | 3- Completed | Build | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0
US-08 | T-305 | Map Visualization | 2026-12-27 | Build | 3- Completed | Build | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0
SPRINT 4 BACKLOG
US-09 | T-401 | Intergrating the Code | 2026-12-29 | 2025-12-29 | Niharika | Integration Test | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-402 | Running and Testing the Code | 2026-12-30 | 2025-12-30 | Niharika | Integration Test | 3- Completed | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-10 | T-403 | Fixing and Final Project | 2025-12-31 | 2025-12-31 | Niharika | System Test | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
US-11 | T-404 | Cross-Browser QA | 2026-01-02 | 2026-01-02 | All | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
US-12 | T-405 | Final Documentation | 2026-01-05 | 2025-01-05 | Renuka, Meghana | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sp 1 | Day 2 | Planning: Initial project planning. | Decision: Concluded to build a Python-heavy project to maximize learning (avoiding simple no-code tools).
Sp 1 | Day 6 | Info: Reviewing the overall Project Structure. | Action: Walkthrough of the folder structure (core/, pages/) so everyone understands the flow.
Sp 2 | Day 16 | Planning: Graphic Plots strategy. | Decision: Decided which specific libraries (Matplotlib/Seaborn) to use for which insights.
Sp 2 | Day 23 | Blocker: Team Confusion on Architecture. | Action: "Clean-the-air" meeting to resolve doubts about where to put logic vs UI code.
Sp 3 | Day 30 | Issue: Frequent merge conflicts overriding code updates. | Action: Niharika enforced "Branch Protection Rules" requiring PR reviews before merge.
Sp 3 | Day 37 | Demo: Teammates proposed new features (Home/About/KYD). | Action: Accepted proposals: Laasya assigned Home/About, Gauri assigned 'Know Your Data' (Numerical Analysis).
Sp 4 | Day 44 | Review: UI Consistency Check (HTML/CSS). | Action: Niharika established global CSS variables to fix table rendering issues.
Sp 4 | Day 51 | Review: Final Draft Demonstration. | Action: Reviewed the nearly-finished product; requested minor preference-based UI tweaks before freezing code.
Sp 4 | Day 56 | Prep: Presentation & Live Demo planning. | Action: Assigned roles for the final presentation: who speaks on Architecture, who does Live Demo, etc.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 2 | 2026-12-21 | 2026-12-21 | All | Writing a clear problem statement and scope before coding | Jumping into development without alignment. | Validating ideas with mentors early. | Finalized problem statement and success criteria.
2 | Sprint 2 | 2026-12-22 | 2026-12-23 | Gauri Joshi | Adding validation and edge-case checks early. | Assuming data is clean or well-formatted. | Using pandas for structured preprocessing. | Implemented data cleaning and preprocessing pipeline.
3 | Sprint 3 | 2026-12-23 | 2026-12-24 | Chanana BC | Creating low-fidelity layout drafts first | Directly copying layouts without understanding flow | Studying reference dashboards for UX ideas. | Built a basic dashboard skeleton.
4 | Sprint 3 | 2026-12-24 | 2026-12-25 | Lassya Kadali | Defining navigation structure upfront | Treating static pages as low priority. | Keeping content minimal and clear. | Implemented Home and About pages with consistent layout.
5 | Sprint 3 | 2026-12-26 | 2026-12-27 | Vinay, Khushi, Krti, Vanshika, Sonika | Selecting libraries based on use-case, not habit. | Overusing libraries for simple logic. | Leveraging pandas, numpy, matplotlib effectively. | Finalized analysis modules using appropriate libraries.
6 | Sprint 3 | 2026-12-27 | 2026-12-28 | Niharika Raut | Validating GeoJSON and projections early. | Ignoring coordinate and projection errors. | Using reliable mapping libraries. | Implemented map visualization with validated GeoJSON.
7 | Sprint 4 | 2026-12-29 | 2026-12-30 | Niharika Raut | Modularizing components before integration. | Hardcoding paths and parameters. | Incremental integration and testing. | Integrated modules with reusable functions.
8 | Sprint 4 | 2026-12-30 | 2026-12-31 | Niharika Raut | Writing test cases alongside development. | Delaying testing until the end. | Logging and tracking bugs systematically. | Fixed major bugs and stabilized the codebase.
9 | Sprint 4 | 2026-12-31 | 2026-01-01 | Renuka, Tanvi, Meghana | Documenting decisions, not just features. | Writing documentation at the last minute. | Keeping docs simple and technical. | Completed final project documentation.
\