## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
BUG-01 | Niharika | 2025-12-29 | Merge Conflict: Logic overwrites in app.py. | Sprint 2 | Niharika | Maintainability | Restricted main branch; enforced 7-branch workflow. | 2026-01-05 | Closed | Process Updated
BUG-02 | Gauri Joushi | 2026-12-22 | Encoding Error: CSVs with special chars failing. | Sprint 2 | Gauri Joushi | Logical | Added latin-1 fallback in utils.py. | 2026-12-22 | Closed | Critical Fix
BUG-03 | Khushi Bhandari | 2026-12-26 | Visuals: Bar charts overlapping. | Sprint 3 | Krti Gautam | User Interface | Adjusted figure size and rotation using Matplotlib params. | 2026-12-27 | Closed | Verified
BUG-04 | Vanshika Jain | 2025-12-27 | Analysis: Complex filters causing slow load. | Sprint 3 | Vinay Manda | Standards | Optimization assistance from AI tools (Claude). | 2025-12-28 | Closed | Optimized
BUG-05 | Chandana BC | 2025-12-28 | UI Glitch: Sidebar overlapping text. | Sprint 3 | Laasya Kadali | User Interface | Applied custom CSS media queries. | 2025-12-28 | Closed | Verified
BUG-06 | Niharika Raut | 2025-12-28 | Map Visibility: Map not loading for certain States. | Sprint 4 | Niharika Raut | Maintainability | Swapped broken GeoJSON with valid Open Source files. | 2026-12-02 | Closed | Fixed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others